## Timeline
This is a guide only, adjust months and tasks as appropriate (see worksheet 2 for an example). Part-time students should add columns as necessary
PhD Timeline
| Year | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
| Month | Feb | March |  | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June
Week
1 | Lit review writing
Send to supervisors
2 | Study 1
Task A
Task B
Task C
Task D
3 | Study 2
Task A
Task B
Task C
Task D
4 | Study 3 - planning
Task A
Task B
Task C
Task D
5 | Thesis writing
Send to supervisors
Editing
intended start
actual start
overtime
on hold due to COVID

## example
| PhD Timeline | [13 empty] | Covid-19
| Year | 2019 | [10 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| Month | March | April |  | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Week
1 | Lit review writing
Send to supervisors
2 | Study 1 recruitment
Data collection (ongoing)
Data analysis
| Write chapter/paper | [11 empty] | Intro + Methods
Send to supervisors/drafting
Publish
3 | Study 2 recruitment
Data collection (ongoing)
Data analysis
| Write chapter/paper | [13 empty] | Intro + Methods | [11 empty] | Results + Discussion
Send to supervisors/authors/drafting
Publish
4 | Systematic review planning
Systematic review writing
Systematic review drafting
Publish review
5 | Study 3 - planning
Data collection/analysis
Writing
Send to authors/drafting
Publish
6 | Thesis writing | [30 empty] | Final discussion/conclusions
Send to supervisors
Editing
intended start
actual start/plan
overtime
on hold due to COVID
if still affected by COVID, stop recruitment and start analysis